## Title Page
AERIS-R ADAPTIVE EXTRUSION RECYCLING AND IN-SITU MANUFACTURING SYSTEM
REQUIREMENTS MANAGEMENT DOCUMENT
NASA LunaRecycle Challenge – Phase 2 Milestone Round
DOCUMENT INFORMATION
Document Title | AERIS-R Requirements Management Document
Document Subtitle | System and Subsystem Requirements – LunaRecycle Phase 2
Document Number | SC-AERIS-RMD-001
Revision | Rev 0 ¦ Initial Release
PROJECT INFORMATION
Program / Project | NASA LunaRecycle Challenge – Phase 2
Contracting Agency | NASA Centennial Challenges
Document Date | March 18, 2026
AUTHORS / CONTRIBUTORS
Team Lead (Systems) | Taha Zaidi, M.Sc – Systems & Requirements Engineering Lead
Principal Investigator | Madison Feehan, B.Com – Founder & CEO, Space Copy Inc.
Strategy / Systems | Swaroopa Shigli, M.Sc – Chief Strategy Officer, Space Copy Inc.
APPROVALS
Role | Name | Signature | Date
Prepared By | Taha Zaidi
Reviewed By | Madison Feehan
Approved By | TBD
Space Copy Inc. ¦ Confidential – For Evaluation Purposes Only

## Revision History
AERIS-R REQUIREMENTS MANAGEMENT DOCUMENT REVISION HISTORY
Document No: SC-AERIS-RMD-001
Rev | Date | Author | Reviewed By | Description of Changes | Affected Sections / Req IDs
Rev 0 | 2026-03-18 | Taha Zaidi | Madison Feehan | Initial release. Requirements matrix populated from LunaRecycle Phase 2 proposal (SPACECOPY_AERIS-R) and Space Copy x Quartus SOW. Includes 94 requirements across System, Subsystem, Assembly, Component, and Software levels. | All – Full document (SC-AERIS-SYS-001 through SC-AERIS-SYS-037; AERIS-R-F-001 through AERIS-R-O-008)
Rev 0.1 | 2026-04-19 | Taha Zaidi | Madison Feehan | Added 14 new PPM Robotic Arm requirements (AERIS-R-PPM-001 through AERIS-R-PPM-014) derived from AERIS FDM System Post-Processing Module: Robotic Arm Technical Overview Rev 0.1. Requirements cover arm platform specs (Desktop/Standard), baseplate mounting, dust sleeve protection, tool changer dust cover, end effector suite (small gripper, large gripper, saw, scraper), thermal trigger logic, IPC/HMI supervisory control architecture, E-stop hardwired integration, PPM subsystem mass budget, and support structure waste recycling interface. Risk IDs R-106 through R-119 assigned. | AERIS-R-PPM-001 through AERIS-R-PPM-014
< To be completed upon next revision >
< To be completed upon next revision >
< To be completed upon next revision >
< To be completed upon next revision >
Space Copy Inc. ¦ SC-AERIS-RMD-001 ¦ Confidential – For Evaluation Purposes Only

## Requirements Matrix
Parent Requirement ID | Requirement ID | Requirement Level | Requirement Type | Requirement Title | Requirement Statement | Rationale / Intent | Source | Affected System Discipline | Affected System/Subsystem/Component Element | Priority | Verification Method | Verification Description | Verification Level | Success Criteria | Risk ID(s) | Compliance Status | Verification Status | Owner | Change History / Notes
N/A – Top-Level System Requirement | SC-AERIS-SYS-001 | Assembly | Functional | Multi-Material AM Capability | The Space Copy system SHALL enable multi-material additive manufacturing in austere and remote environments. | Core mission objective defined in SOW. | Space Copy x Quartus SOW | Entire System Unit | Entire Printer System | 1-Critical | Demonstration | Operational demonstration in representative environment | System | Successful fabrication of multi-material part | R-001 | Draft | Not started | Systems / Requirements Engineering Lead | Initial seed requirement
SC-AERIS-SYS-001 | SC-AERIS-ENV-002 | System | Environmental | Operating Temperature Range | The system SHALL operate within a temperature range of -40°C to +40°C. (-40°F to +104°F) | Supports disaster response, Arctic, and lunar analog operations. | Space Copy x Quartus SOW | Thermal | Gantry/Enclosure | 1-Critical | Test | Thermal chamber operational test | Subsystem | No functional degradation across temperature range | R-004 | Draft | Not started | Thermal Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-MFG-003 | Subsystem | Performance | Multi-Material Print Support | The system SHALL support printing with at least two distinct material classes within a single build. | Enables structural and functional part fabrication. | Space Copy x Quartus SOW | Manufacturing Process | Extrusion System | 1-Critical | Test | Multi-material print validation test | Subsystem | Dimensional and material integrity met | R-007 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SW-004 | Software | Reliability | Autonomous Fault Recovery | The system SHALL autonomously detect and recover from print faults without human intervention. | Required for remote and space-based operations. | Space Copy x Quartus SOW | Software | Firmware / Embedded Software | 2-High | Analysis | Fault injection during simulation | Subsystem | Successful recovery from ≥90% of injected faults | R-012 | Draft | Not started | Software Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-LOG-005 | System | Maintainability | Logistics Transportability | The system SHALL be transportable by standard ground and air logistics platforms. | Supports rapid deployment to disaster zones. | Space Copy x Quartus SOW | Structure | Structural Frame | 2-High | Inspection | Dimensional and weight inspection | System | Meets size and mass constraints | R-015 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-006 | System | Functional | Multi-Material Manufacturing | The system SHALL manufacture polymer, metallic, ceramic (and/or composite), and ISRU parts using | Broad material capability is core to ISRU and disaster-response missions requiring on-demand part production. | Space Copy | Manufacturing Process | Extrusion System | 1-Critical | Analysis | Fabricate representative coupons from each material class and verify dimensional and mechanical properties. | System | Successful part production from ≥3 distinct material classes | R-016 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-007 | System | Functional | Dimensionally Repeatable Part Production | The system SHALL produce dimensionally repeatable and mechanically functional parts suitable for | Mission-critical parts require dimensional consistency across batches to ensure fit, form, and function. | Space Copy | End-Use Part (EUP) | Entire Printer System | 1-Critical | Analysis | Print identical geometry five consecutive times; measure dimensional variance and verify ≤specified tolerance. | System | Part-to-part dimensional variation within specified tolerance for ≥5 consecutive prints | R-017 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-008 | System | Functional | Autonomous and Crew-Assisted Operation | The system SHALL support autonomous and crew-assisted operation with a simple user interface. | Reduces training burden and enables operation by non-specialist crew in remote or space environments. | Space Copy | Operations | User Interface (HMI) | 2-High | Analysis | Demonstrate full print cycle in autonomous mode; repeat with crew input via UI without additional training. | System | Successful unassisted cycle completion and crew-directed cycle with no errors | R-018 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-009 | System | Functional | CAD File and Material Profile Ingestion | The system SHALL accept pre-validated digital part (CAD) files and material profiles and be able to | Enables on-demand production directly from design data, reducing operator skill requirements. | Space Copy | Software | Firmware / Embedded Software | 1-Critical | Analysis | Upload standard CAD file and material profile; verify automatic G-code generation and successful print initiation. | Subsystem | Error-free G-code generation and print initiation from uploaded CAD/profile within defined time limit | R-019 | Draft | Not started | Software Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-010 | System | Functional | Print Health and Status Monitoring | The system SHALL monitor print health and system status during operation with the use of sensors | Enables fault detection and operator awareness, especially critical during autonomous operation. | Space Copy | Controls | Sensors & Instrumentation | 1-Critical | Analysis | Inject simulated sensor fault conditions and verify real-time alert generation and logging. | Subsystem | 100% anomaly detection and alert output for injected fault conditions | R-020 | Draft | Not started | Sensors & Calibration Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-011 | System | Functional | Operational Data Logging and Downlink | The system SHALL log operational data for post-process analysis and downlink via an | Enables remote diagnostics, trend analysis, and mission debrief without crew involvement. | Space Copy | Communications | Data Handling / Logging | 2-High | Analysis | Complete a print cycle and verify full data log is stored locally and successfully transmitted via designated comm interface. | Subsystem | Complete cycle log retrievable locally and via downlink with no data loss | R-021 | Draft | Not started | Software Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-012 | System | Operation | Non-Expert Operability | The system SHALL be operable by non-expert users with minimal training. An instruction manual and | Critical for disaster response and remote deployments where trained engineers are unavailable. | Space Copy | Operations | User Interface (HMI) | 2-High | Analysis | Untrained operator completes full print cycle using only provided instruction manual within defined time limit. | System | Untrained operator completes cycle successfully within allotted time with no system errors | R-022 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-013 | System | Operation | Minimized Crew Time During Printing | The system SHALL minimize required crew time during printing operations. | Crew time is a scarce resource in space and disaster environments; autonomous operation reduces burden. | Space Copy | Operations | Entire Printer System | 2-High | Analysis | Time crew involvement across a full print cycle and verify active crew time does not exceed defined threshold. | System | Active crew time per cycle ≤ defined maximum (e.g., 20 minutes per cycle) | R-023 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-014 | System | Operation | Remote Monitoring and Commanding | The system SHALL support remote monitoring and commanding where communications allow. | Enables mission control oversight and intervention without crew proximity to the system. | Space Copy | Communications | Communications Interface | 2-High | Analysis | Demonstrate full print cycle monitoring and pause/resume command from remote terminal via available link. | System | Successful remote command execution and real-time telemetry receipt during print cycle | R-024 | Draft | Not started | Controls & Firmware Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-015 | System | Operation | Constrained Resource Budget Compliance | The system SHALL operate within constrained power, volume, and thermal budgets of host platforms, | Host platform resources (power, volume, heat dissipation) are limited; compliance prevents mission conflicts. | Space Copy | Entire System Unit | Entire Printer System | 1-Critical | Analysis | Verify system power draw, envelope dimensions, and heat dissipation against host platform budget allocations via analysis and test. | System | All resource budgets satisfied with defined margin per ICD | R-025 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-016 | System | Operation | Mission Workflow Integration | The system SHALL integrate into crewed and uncrewed mission workflows without introducing | Ensures the manufacturing system does not disrupt primary mission activities or crew safety. | Space Copy | Operations | Entire Printer System | 2-High | Analysis | Conduct operational concept review; verify no mission timeline conflicts or safety hazards during integrated operations. | System | No identified unmitigated safety or schedule conflicts in integrated mission scenario review | R-026 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-017 | System | Environmental | Launch Vibration and Shock Survivability | The system SHALL survive launch vibration and shock environments. | All spaceflight hardware must withstand launch loads without damage or performance degradation. | Space Copy | Structure | Structural Frame | 1-Critical | Analysis | Subject system or representative structural test article to qualification-level vibration and shock per applicable launch vehicle ICD. | System | No structural failure, no functional degradation post-test; all alignment and calibration within acceptance limits | R-027 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-018 | System | Environmental | Multi-Sector Deployment Survivability | The system SHALL survive deployment into the following sectors: Manufacturing, Construction & | Commercial and government customers operate in diverse and harsh environments; platform must be broadly deployable. | Space Copy | Entire System Unit | Gantry/Enclosure | 2-High | Analysis | Demonstrate or analyze survivability for representative environmental conditions across each target sector. | System | No unmitigated failure modes identified for any target deployment sector | R-028 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-019 | System | Environmental | Gravity-Independent Operation | The system SHALL operate in microgravity, partial gravity, and 1g environments. | Supports ISS, lunar, Martian, and terrestrial applications with a single platform architecture. | Space Copy | Mechanical | Gantry/Enclosure | 1-Critical | Analysis | Analyze material flow, extrusion, and motion system performance in each gravity regime; validate via test where feasible. | System | No gravity-dependent failure modes identified; material flow and deposition verified across all regimes | R-029 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-020 | System | Environmental | Internal Thermal Condition Control | The system SHALL maintain controlled internal thermal conditions to ensure print quality and | Print quality is sensitive to thermal gradients; hardware reliability requires controlled thermal environment. | Space Copy | Thermal | Thermal Control System | 1-Critical | Analysis | Operate system across defined ambient temperature range and verify internal chamber temperature remains within specified bounds. | Subsystem | Internal chamber temperature within ±5°C of setpoint across full operating ambient range | R-030 | Draft | Not started | Thermal Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-021 | System | Environmental | Radiation Tolerance | The system SHALL tolerate elevated radiation environments consistent with spaceflight missions. | Electronics and materials must withstand total ionizing dose and single-event effects for mission duration. | Space Copy | Entire System Unit | Control Electronics | 2-High | Analysis | Conduct radiation dose analysis for electronics; verify parts compliance with total ionizing dose and SEE requirements. | System | All electronics radiation-qualified to mission TID and SEE requirements | R-031 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-022 | System | Environmental | Dust and Particulate Intrusion Mitigation | The system SHALL mitigate dust and particulate intrusion for terrestrial and planetary surface | Lunar and Martian regolith and terrestrial dust can damage mechanisms and contaminate electronics. | Space Copy | Mechanical | Environmental Control / Enclosure | 1-Critical | Analysis | Expose system to representative dust environment and verify no ingress to protected zones; confirm continued operation. | System | No functional degradation after dust exposure test; critical interfaces remain clean | R-032 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-023 | System | Environmental | Crewed Environment Safety | The system SHALL be safe for operation in crewed environments, including control of hot surfaces, | Crew safety is non-negotiable; all hazards must be designed out or mitigated to acceptable risk levels. | Space Copy | Entire System Unit | Safety System | 1-Critical | Analysis | Complete hazard analysis (PHA/SHA) and verify all identified hazards are mitigated to acceptable risk per applicable safety standard. | System | All hazards mitigated to Severity ≤ Category II / Probability ≤ Level C per applicable standard | R-033 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-024 | System | Interface | Mechanical Interface with Host Platform | The system SHALL interface mechanically with standardized mounting points of host platforms. | Standardized mechanical interfaces enable cross-platform deployment without custom structural modifications. | Space Copy | Structure | Structural Frame | 2-High | Analysis | Verify mounting dimensions and load ratings against defined host platform interface standard. | Assembly | All mechanical interface dimensions and load ratings within ICD-specified tolerances | R-034 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-025 | System | Interface | Electrical Interface with Host Power System | The system SHALL interface electrically with host power systems using defined voltage and current | Defined power interface prevents overload and ensures compatibility with host platform distribution architecture. | Space Copy | Power | Power System | 1-Critical | Analysis | Connect system to host-representative power supply; verify stable operation across defined voltage and current limits. | Subsystem | System operates nominally across full specified input voltage and current range with no faults | R-035 | Draft | Not started | Electrical / Power Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-026 | System | Interface | Data System Interface | The system SHALL interface with host data systems for command, telemetry, and data transfer. | Integrated data interface enables mission control visibility and command authority over manufacturing operations. | Space Copy | Communications | Data Handling / Logging | 2-High | Analysis | Verify bidirectional data exchange, command execution, and telemetry receipt via defined host data interface. | Subsystem | 100% command execution and telemetry receipt with no data corruption at defined interface rates | R-036 | Draft | Not started | Controls & Firmware Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-027 | System | Interface | Modular Subsystem Integration | The system SHALL support modular integration and replacement of subsystems where feasible. | Modularity reduces maintenance time, enables upgrades, and supports logistics efficiency for long-duration missions. | Space Copy | Mechanical | Entire Printer System | 2-High | Analysis | Remove and reinstall each designated modular subsystem; verify system returns to nominal operation within defined time. | System | Each modular subsystem replaceable by one technician within defined time with standard tools only | R-037 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-028 | System | Interface | Reliability-First Design Philosophy | The system design SHALL prioritize reliability and qualification over unnecessary novelty. | Novel unproven components increase mission risk; heritage-based design reduces qualification burden. | Space Copy | Entire System Unit | Entire Printer System | 2-High | Analysis | Review design trade studies and component selection rationale; confirm novel components have defined qualification path. | System | All novel components have documented qualification plan; heritage components used where feasible | R-038 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-029 | System | Performance | Heritage FDM Component Usage | The system SHALL leverage heritage FDM principles and proven components where feasible. | Heritage components reduce development risk, lower cost, and benefit from existing qualification data. | Space Copy | Manufacturing Process | Extrusion System | 2-High | Analysis | Review BOM and identify heritage vs. novel components; verify justification for any non-heritage selection. | System | ≥50% of mechanical and electrical components by count are heritage or COTS qualified items | R-039 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-030 | System | Operation | Cost Effectiveness vs. Launch Mass | The system SHALL be cost-effective relative to launching equivalent spare mass. | Economic justification for in-situ manufacturing depends on producing parts at lower cost than Earth supply. | Space Copy | Entire System Unit | Entire Printer System | 2-High | Analysis | Develop life-cycle cost model comparing AERIS-R production cost per kg to equivalent launch-to-destination cost. | System | AERIS-R production cost per kg < delivery cost of equivalent replacement mass to deployment site | R-040 | Draft | Not started | Program Manager | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-031 | System | Safety | Regulatory and Safety Standards Compliance | The system SHALL comply with applicable spaceflight, safety, and regulatory standards. (For the case | Regulatory compliance is required for mission approval, crew safety certification, and partner acceptance. | Space Copy | Entire System Unit | Safety System | 1-Critical | Analysis | Complete compliance matrix against all applicable standards; resolve all non-compliances via waiver or design change. | System | 100% of applicable standard requirements are compliant or have approved waivers | R-041 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-032 | System | Performance | Incremental Capability Upgrade Path | The system SHALL support incremental capability upgrades aligned with program schedules. | Program roadmap requires phased capability expansion; modular architecture must accommodate upgrades without redesign. | Space Copy | Entire System Unit | Entire Printer System | 3-Medium | Analysis | Review system architecture for defined upgrade interfaces; confirm at least one planned upgrade is demonstrated end-to-end. | System | Defined upgrade interfaces exist and at least one capability upgrade demonstrated without system-wide redesign | R-042 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-033 | System | Operation | Repeatable Part Production in Target Environments | The system SHALL demonstrate repeatable production of usable parts in target environments. | Repeatability across environment and cycle is the fundamental measure of manufacturing system maturity. | Space Copy | End-Use Part (EUP) | Entire Printer System | 1-Critical | Test | Execute ≥5 consecutive production cycles in representative environment; measure part properties against acceptance criteria. | System | ≥80% of parts across all cycles pass dimensional and mechanical acceptance criteria | R-043 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-034 | System | Operation | Extended Low-Maintenance Operation | The system SHALL operate for extended periods with minimal maintenance. | Long-duration missions cannot tolerate frequent maintenance requiring resupply of spares or crew time. | Space Copy | Entire System Unit | Maintenance | 2-High | Test | Operate system continuously for defined duration; record all maintenance events and verify frequency is within specified limit. | System | Unscheduled maintenance events ≤ defined threshold per 1000 operating hours | R-044 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-035 | System | Safety | Crewed Mission Safety and Reliability | The system SHALL meet safety and reliability requirements for crewed missions. | NASA and other agency standards impose specific safety and reliability thresholds for equipment operating near crew. | Space Copy | Entire System Unit | Safety System | 1-Critical | Test | Perform reliability analysis (FMEA/FMECA) and safety analysis; verify all critical failure modes are mitigated. | System | System MTBF ≥ defined mission duration; all Catastrophic and Critical hazards eliminated or mitigated | R-045 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-036 | System | Performance | Technology Readiness Level Achievement | The system SHALL achieve targeted Technology Readiness Level milestones. | TRL milestones are required for NASA program phases and commercial investment gates. | Space Copy | Entire System Unit | Entire Printer System | 2-High | Test | Conduct TRL assessment at each program gate; document evidence package supporting claimed TRL. | System | TRL assessment confirms target level with documented evidence per NASA TRL definitions | R-046 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | SC-AERIS-SYS-037 | System | Operation | Mission Partner Acceptance | The system SHALL be accepted by mission partners as an operationally valuable manufacturing | Mission partner buy-in is required for operational deployment; system must meet partner-defined utility criteria. | Space Copy | Entire System Unit | Entire Printer System | 3-Medium | Test | Conduct partner acceptance review; demonstrate system capabilities against partner-defined use cases and success criteria. | System | Mission partner signs acceptance documentation confirming operational value | R-047 | Draft | Not started | Program Manager | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-001 | Subsystem | Functional | Eligible Feedstock Processing | The system SHALL accept and process Zotek F30 Aviation foam (PVDF closed-cell foam) as the primary eligible trash feedstock. | Per LunaRecycle Challenge rules; Zotek F30 is the sole eligible item. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Test / Inspection | Load 0.500 kg Zotek F30 foam into MBU; confirm system accepts material and initiates processing sequence. | Subsystem | System accepts Zotek F30 input and initiates beneficiation with no errors | R-050 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-002 | Subsystem | Functional | Minimum Batch Mass | The system SHALL process a minimum batch of 0.500 kg of Zotek F30 foam per operating cycle. | 500 g minimum per challenge requirement. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Test / Measurement | Weigh input foam batch before processing; verify system processes full 0.500 kg minimum without rejection. | Subsystem | ≥0.500 kg Zotek F30 foam processed per cycle with no mass loss prior to extrusion | R-051 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-003 | Subsystem | Functional | Regolith Integration | The system SHALL accept highlands lunar regolith simulant as a secondary input and homogeneously combine it with processed Zotek F30 foam at a ratio of approximately 85% regolith / 15% foam by mass. | Regolith excluded from mass efficiency calculation per challenge rules. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Test / Analysis | Measure output composite sample composition via mass balance; verify regolith:foam ratio within ±2% of 85:15 target. | Subsystem | Composite mixture is 85 ±2% regolith by mass; visually and analytically homogeneous | R-052 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-004 | Component | Functional | Material Shredding | The Material Beneficiation Unit (MBU) SHALL shred Zotek F30 foam to a particle size of less than 2 mm. | Required for consistent feedstock and extrusion quality. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Test / Inspection | Sample output from shredder stage; measure particle size distribution via sieve analysis. | Component | 100% of particles pass 2 mm sieve; D90 ≤ 2 mm confirmed | R-053 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-005 | Component | Functional | Feedstock Mixing | The MBU SHALL produce a homogeneous foam-regolith feedstock mixture suitable for FDM extrusion. | Mixing auger at variable 50–200 RPM. | Space Copy/LunaRecycle | Manufacturing Process | Mixer/Annealing | 1-Critical | Test / Analysis | Extract feedstock sample post-mixing; verify spatial homogeneity via visual inspection and density measurement at multiple locations. | Component | Foam-regolith mass ratio uniform to ±3% across sampled locations; no visible segregation | R-054 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-006 | System | Functional | Additive Manufacturing Output | The system SHALL produce usable outputs via fused deposition modeling (FDM), including interlocking construction bricks, precision tools and repair parts, and structural components. | Three output categories per cycle. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 1-Critical | Test / Inspection | Run full production cycle; weigh and inspect each output category and verify all three categories are produced. | System | Interlocking bricks, tools/repair parts, and structural components all produced with no missing output category | R-055 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-007 | Component | Functional | Support Structure Recycling | The system SHALL collect support structure waste for recycling into subsequent batches. | 0.050 kg support structures recyclable per cycle. | Space Copy/LunaRecycle | Manufacturing Process | Waste Handling / Recycling Module | 2-High | Inspection | Inspect support structure collection bin after cycle; verify all support waste is captured and not discarded. | Component | All support structures captured in designated recycling bin; 0 kg discarded as waste | R-056 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-008 | System | Functional | Automated Cycle Execution | The system SHALL execute all manufacturing phases (beneficiation, extrusion, cooling, post-processing) autonomously after initial operator loading. | Operator interaction limited to 20 min/cycle for loading and retrieval. | Space Copy/LunaRecycle | Controls | Firmware / Embedded Software | 1-Critical | Demonstration | Initiate full cycle after operator loading; monitor for any unsolicited operator prompts during manufacturing phases. | System | Zero operator interventions required between initial load and part extraction across ≥3 consecutive cycles | R-057 | Draft | Not started | Controls & Firmware Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-009 | Subsystem | Functional | Post-Processing Operations | The Post-Processing Module (PPM) SHALL perform automated support structure removal and surface finishing on all printed parts. | 4-axis robotic arm with coupled end effector. | Space Copy/LunaRecycle | Manufacturing Process | Robotic Arm | 2-High | Test / Demonstration | Run PPM on representative printed part; verify support removal completeness and surface finish quality. | Subsystem | All designated support structures removed; surface roughness within specified acceptance band | R-058 | Draft | Not started | Motion Systems Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-F-010 | Subsystem | Functional | Particulate Capture | The system SHALL capture all regolith and process-generated particulate waste via an integrated HEPA-filtered vacuum system. | Fine particles <10 μm present respiratory hazard. | Space Copy/LunaRecycle | Manufacturing Process | Waste Handling / Recycling Module | 1-Critical | Inspection / Test | Operate shredding/mixing cycle with regolith simulant; inspect downstream components and air quality sensor for particulate breakthrough. | Subsystem | No particulate detected downstream of HEPA filter; all generated dust captured within enclosure | R-059 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-001 | System | Performance | Total System Mass | The total system mass SHALL NOT exceed 50 kg. | Verified on calibrated scale per success criteria. | Space Copy/LunaRecycle | Entire System Unit | Entire Printer System | 1-Critical | Measurement (calibrated scale) | Weigh fully integrated system on calibrated scale prior to acceptance test; compare to 50 kg limit. | System | Measured total system mass ≤ 50.0 kg on calibrated scale | R-060 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-002 | System | Performance | Cycle Time | The system SHALL complete one full recycling cycle within 210 minutes (3.5 hours). | Includes all 6 sequential phases. | Space Copy/LunaRecycle | Manufacturing Process | Entire Printer System | 1-Critical | Test / Timing | Time each phase of a complete recycling cycle; sum total elapsed time from material load to part extraction. | System | Total elapsed time from material loading to part output ≤ 210 minutes | R-061 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-003 | Subsystem | Performance | Peak Power Consumption | The system peak power consumption SHALL NOT exceed 2.0 kW. | Peak occurs during extrusion phase. | Space Copy/LunaRecycle | Power | Power System | 1-Critical | Test / Measurement | Monitor instantaneous power draw via calibrated power meter throughout full cycle; record peak value. | Subsystem | Peak instantaneous power draw ≤ 2.0 kW at any point during full cycle | R-062 | Draft | Not started | Electrical / Power Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-004 | Subsystem | Performance | Average Operating Power | The system average operating power SHALL NOT exceed 1.5 kW. | Total energy per cycle: 4.5 kWh. | Space Copy/LunaRecycle | Power | Power System | 2-High | Test / Measurement | Compute average power from energy meter data across full cycle; verify against 1.5 kW limit. | Subsystem | Cycle-averaged power ≤ 1.5 kW; total energy per cycle ≤ 4.5 kWh | R-063 | Draft | Not started | Electrical / Power Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-005 | System | Performance | Mass Efficiency | The system SHALL achieve a mass efficiency of at least 600%, calculated as usable output mass (kg) divided by eligible trash input mass (kg), excluding regolith. | Design target: 650% (3.25 kg out / 0.500 kg in). | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 1-Critical | Test / Calculation | Weigh total usable output and input foam mass; calculate mass efficiency = usable output (kg) ÷ foam input (kg) × 100%. | System | Calculated mass efficiency ≥ 600% (target 650%) for each complete cycle | R-064 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-006 | System | Performance | Energy Efficiency | The system SHALL achieve an energy efficiency of at least 0.6 kg/kWh, calculated as usable output mass divided by total electricity consumed. | Design target: 0.72 kg/kWh. | Space Copy/LunaRecycle | Manufacturing Process | Entire Printer System | 1-Critical | Test / Calculation | Measure total energy consumed per cycle via power meter; divide total usable output mass by energy consumed. | System | Energy efficiency ≥ 0.6 kg/kWh (target 0.72 kg/kWh) per cycle | R-065 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-007 | System | Performance | Usable Output Mass per Cycle | The system SHALL produce a minimum of 3.25 kg total usable output per cycle, distributed as: interlocking bricks ≥2.00 kg, tools/repair parts ≥0.80 kg, structural components ≥0.45 kg. | Based on 0.500 kg foam + 2.83 kg regolith input per cycle. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 1-Critical | Test / Measurement | Weigh all usable outputs by category at end of cycle; verify each category and total meet minimum mass. | System | Interlocking bricks ≥ 2.00 kg; tools/repair parts ≥ 0.80 kg; structural components ≥ 0.45 kg; total ≥ 3.25 kg | R-066 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-008 | Component | Performance | Compressive Strength of Outputs | Produced components SHALL achieve a minimum compressive strength of 25 MPa, verified per ASTM C109. | Design prediction: 25–35 MPa at 85% regolith content. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 1-Critical | Test (ASTM C109) | Test 1-in-10 samples per ASTM C109 compressive test method; verify mean and minimum values against 25 MPa threshold. | Component | All tested samples meet ≥ 25 MPa compressive strength; mean value ≥ 30 MPa | R-067 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-009 | Component | Performance | Flexural Strength of Outputs | Produced components SHALL achieve a minimum flexural strength of 10 MPa, verified per ASTM C78. | Target >15 MPa for interlayer bonding. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 2-High | Test (ASTM C78) | Test 1-in-10 samples per ASTM C78 flexural test method; verify mean and minimum values against 10 MPa threshold. | Component | All tested samples meet ≥ 10 MPa flexural strength; mean value ≥ 15 MPa | R-068 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-010 | Component | Performance | Dimensional Accuracy – Structural Components | Structural output components SHALL meet dimensional tolerances of ±0.5 mm relative to CAD specifications. | Structural tolerance of ±0.5 mm ensures interlocking brick and bracket assemblies fit correctly on first assembly. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 2-High | Inspection / Measurement (caliper) | Measure all critical dimensions of structural output parts with calibrated calipers; compare to CAD nominal. | Component | All critical structural dimensions within ±0.5 mm of CAD nominal across ≥5 sampled parts | R-069 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-011 | Component | Performance | Dimensional Accuracy – Precision Parts | Precision tool and repair part outputs SHALL meet dimensional tolerances of ±0.2 mm relative to CAD specifications. | Dimensional accuracy ensures fit and function for structural part assemblies; tolerance derived from LunaRecycle output performance targets. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 2-High | Inspection / Measurement (caliper) | Measure all critical dimensions of precision tool and repair part outputs with calibrated calipers. | Component | All critical precision part dimensions within ±0.2 mm of CAD nominal across ≥5 sampled parts | R-070 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-012 | Component | Performance | Extrusion Temperature Range | The extruder SHALL maintain a melt temperature within the range of 180–220°C during active printing, with a variation not exceeding ±2°C. | PVDF decomposes above 300°C; lower bound ensures melt quality. | Space Copy/LunaRecycle | Thermal | Extrusion System | 1-Critical | Test / Measurement | Log extruder barrel thermocouple data at 1 Hz throughout print phase; verify range and variation. | Component | Extruder temperature within 180–220°C range; variation ≤ ±2°C throughout active print phase | R-071 | Draft | Not started | Thermal Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-013 | Component | Performance | Build Platform Temperature | The heated build platform SHALL maintain a temperature within the range of 80–100°C during printing. | Heated build platform temperature ensures first-layer adhesion of foam-regolith composite and prevents warping. | Space Copy/LunaRecycle | Thermal | Build Platform / Print Bed | 2-High | Test / Measurement | Log build platform thermocouple data throughout print phase; verify temperature within 80–100°C. | Component | Build platform temperature within 80–100°C range throughout active print phase | R-072 | Draft | Not started | Thermal Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-014 | Component | Performance | Layer Resolution | The FDM Core SHALL support a selectable layer height in the range of 0.2–0.8 mm. | Typical operating layer height: 0.4 mm. | Space Copy/LunaRecycle | Manufacturing Process | Extrusion System | 2-High | Inspection / Test | Configure layer height to minimum (0.2 mm) and maximum (0.8 mm) settings; verify print execution at both extremes. | Component | System successfully executes prints at 0.2 mm and 0.8 mm layer heights with acceptable part quality | R-073 | Draft | Not started | Manufacturing Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-015 | Component | Performance | Positioning Accuracy | The Cartesian gantry motion system SHALL achieve a positioning accuracy of ±0.1 mm. | Gantry positioning accuracy of ±0.1 mm is required to achieve the dimensional tolerances specified for output parts. | Space Copy/LunaRecycle | Controls | Motion System (X/Y/Z) | 1-Critical | Test / Measurement | Command gantry to defined grid of positions; measure actual position with calibrated reference gauge. | Component | Actual position error ≤ ±0.1 mm at all measured points across full build volume | R-074 | Draft | Not started | Motion Systems Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-016 | Component | Performance | Build Volume | The FDM Core build volume SHALL be at minimum 226.3 × 226.3 × 366 mm. | Build volume must accommodate the largest specified output geometry (interlocking brick dimensions per Figure 1). | Space Copy/LunaRecycle | Manufacturing Process | Extrusion System | 2-High | Inspection / Measurement | Measure internal build envelope dimensions with calibrated tape or laser tool; confirm all three axes meet minimum. | Component | Measured build volume ≥ 226.3 × 226.3 × 366 mm in each axis | R-075 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-017 | Subsystem | Performance | Chamber Thermal Uniformity | The closed-chamber design SHALL maintain a temperature differential of less than 5°C across the build volume during active printing. | Double-wall insulation reduces heat loss 70% vs. open-frame. | Space Copy/LunaRecycle | Thermal | Environmental Control / Enclosure | 2-High | Test / Analysis (FEA) | Place thermocouples at multiple locations in build volume during print; verify max differential across all sensors. | Subsystem | Temperature differential < 5°C across all thermocouple locations during active print | R-076 | Draft | Not started | Thermal Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-018 | System | Performance | Crew Time per Cycle | The system SHALL require no more than 20 minutes of crew time per operating cycle. | 1 crew member for loading, monitoring, and part retrieval. | Space Copy/LunaRecycle | Operations | Entire Printer System | 2-High | Test / Demonstration | Time all crew activities from material loading to part retrieval; sum active crew time per cycle. | System | Total active crew time per cycle ≤ 20 minutes | R-077 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-019 | System | Performance | Water Consumption | The system SHALL require zero water input per operating cycle. | Process is entirely dry. | Space Copy/LunaRecycle | Manufacturing Process | Entire Printer System | 1-Critical | Inspection / Analysis | Review process design documentation and inspect water connection points; confirm no water input is incorporated. | System | No water input connections present; process water consumption = 0 kg per cycle confirmed by inspection | R-078 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-P-020 | System | Performance | Consecutive Cycle Reliability | The system SHALL execute a minimum of three consecutive complete cycles without operator intervention beyond initial loading. | Final Round readiness criterion. | Space Copy/LunaRecycle | Manufacturing Process | Entire Printer System | 1-Critical | Demonstration | Execute three consecutive full production cycles; log any operator interventions beyond initial loading. | System | Three consecutive cycles completed with zero unscheduled operator interventions | R-079 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-I-001 | System | Interface | Electrical Power Interface | The system SHALL operate on a single-phase AC electrical supply consistent with habitat power infrastructure, drawing no more than 2.0 kW peak. | No power generation capability; net energy consumption only. | Space Copy/LunaRecycle | Power | Power System | 1-Critical | Test / Inspection | Connect system to host-representative AC supply; verify stable operation and measure peak power draw. | System | System operates nominally on single-phase AC; peak draw ≤ 2.0 kW confirmed by measurement | R-080 | Draft | Not started | Electrical / Power Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-I-002 | Component | Interface | Input Material Interface – Foam | The Material Beneficiation Unit input hopper SHALL accommodate up to 1.0 kg of Zotek F30 Aviation foam per cycle. | Input hopper foam capacity of 1.0 kg provides 2× margin over the minimum 0.500 kg batch to allow flexibility in loading. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Inspection / Measurement | Measure foam input hopper internal volume and verify it accommodates 1.0 kg of Zotek F30 without overflow. | Component | Input hopper accepts 1.0 kg Zotek F30 foam without overflow or jamming | R-081 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-I-003 | Component | Interface | Input Material Interface – Regolith | The Material Beneficiation Unit input hopper SHALL accommodate up to 4.0 kg of highlands lunar regolith simulant per cycle. | Hopper must hold a full-cycle regolith batch to enable uninterrupted beneficiation without top-up. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Inspection / Measurement | Measure regolith input hopper volume; verify it accepts 4.0 kg of highlands lunar regolith simulant. | Component | Input hopper accepts 4.0 kg regolith simulant without overflow or bridging | R-082 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-I-004 | Component | Interface | Output Collection Interface | The system SHALL provide an accessible output bin for finished parts transferred from the Post-Processing Module. | Automated conveyor transfer from PPM to bin. | Space Copy/LunaRecycle | Operations | Entire Printer System | 2-High | Inspection | Inspect output bin location and opening dimensions; verify crew member can retrieve parts without tools. | Component | Output bin accessible by one crew member with no special tools; parts removable without damage | R-083 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-I-005 | Subsystem | Interface | Control Software Interface | The system SHALL accept G-code programs for print geometry selection prior to each manufacturing phase. | G-code is the industry-standard machine instruction format for FDM systems; compatibility ensures interoperability with standard slicer software. | Space Copy/LunaRecycle | Software | Firmware / Embedded Software | 2-High | Test / Demonstration | Upload standard G-code file to control interface; verify system parses and executes file without error. | Subsystem | G-code file accepted and executed without errors; print initiates within 60 seconds of upload | R-084 | Draft | Not started | Software Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-001 | System | Safety | Exterior Surface Temperature | The exterior accessible surfaces of the system SHALL be maintained at or below 45°C during operation. | Enclosed chamber with thermal interlocks required. | Space Copy/LunaRecycle | Thermal | Environmental Control / Enclosure | 1-Critical | Test / Measurement | Operate system at steady state; measure exterior surface temperatures at all accessible locations with contact thermometer. | System | All accessible exterior surfaces ≤ 45°C during steady-state operation | R-085 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-002 | Component | Safety | Thermal Interlock – Overtemperature | The system SHALL incorporate thermal interlocks that prevent extruder temperature from exceeding 280°C to remain below PVDF (Zotek F30) decomposition threshold. | HF release risk above 300°C; 20°C margin applied. | Space Copy/LunaRecycle | Thermal | Extrusion System | 1-Critical | Test / Inspection | Command extruder above 280°C setpoint via fault injection; verify interlock activates and cuts heater power. | Component | Heater power cut and alarm triggered before extruder temperature reaches 280°C | R-086 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-003 | Component | Safety | Off-Gas Capture | The system SHALL incorporate an activated carbon filter to capture trace emissions from PVDF processing. | PVDF off-gas products including HF are hazardous in crewed environments; activated carbon filtration is required as a secondary barrier. | Space Copy/LunaRecycle | Manufacturing Process | Environmental Control / Enclosure | 1-Critical | Inspection / Test | Operate system with PVDF feedstock at operating temperature; sample exhaust air downstream of carbon filter for HF and organic compounds. | Component | HF and VOC concentrations downstream of filter below OSHA/SMAC threshold limits | R-087 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-004 | Component | Safety | Dust Containment – HEPA Filtration | The system SHALL operate under a sealed, HEPA-filtered negative pressure enclosure to prevent release of regolith particulates <10 μm. | Fine regolith dust is a respiratory hazard. | Space Copy/LunaRecycle | Manufacturing Process | Environmental Control / Enclosure | 1-Critical | Inspection / Test | Operate MBU shredding cycle; sample air outside enclosure for particles < 10 μm using particle counter. | Component | Particle count outside enclosure remains below ambient baseline; no HEPA breakthrough detected | R-088 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-005 | Component | Safety | Mechanical Guarding – Shredder | The rotating shredder assembly SHALL be fully enclosed with interlocked access panels that prevent blade operation when the enclosure is open. | Shredder blades rotating at 500 RPM present a severe laceration hazard; interlocked guarding is required by applicable machine safety standards. | Space Copy/LunaRecycle | Mechanical | Material Beneficiation Processing Unit | 1-Critical | Inspection / Test | Open shredder access panel while system is powered; verify shredder blades do not activate. | Component | Shredder motor does not energize with access panel open; interlock confirmed by ≥3 open/close cycles | R-089 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-006 | System | Safety | Emergency Stop | The system SHALL incorporate an emergency stop (E-stop) that immediately halts all motion and heating when activated. | Motion inhibit must engage during door-open condition. | Space Copy/LunaRecycle | Controls | Safety System | 1-Critical | Test / Demonstration | Activate E-stop during active print and during motion; verify all motion and heaters cease within defined response time. | System | All motion and heater power ceases within 500 ms of E-stop activation; system latches off until manual reset | R-090 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-S-007 | System | Safety | Pressure Vessel Exclusion | The system SHALL NOT incorporate any pressure vessel operating above 15 psig. | All pathways at atmospheric or slight negative pressure. | Space Copy/LunaRecycle | Mechanical | Entire Printer System | 1-Critical | Analysis / Inspection | Review engineering drawings and inspect all fluid and gas pathways; confirm no pressure vessel above 15 psig. | System | No pressure vessel operating above 15 psig identified; all pathways confirmed at atmospheric or negative pressure | R-091 | Draft | Not started | Safety & Reliability Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-C-001 | System | Constraint | Total Mass Constraint | The integrated AERIS-R system mass SHALL NOT exceed 50 kg. | Hard challenge rule constraint. | Space Copy/LunaRecycle | Entire System Unit | Entire Printer System | 1-Critical | Measurement (calibrated scale) | Weigh fully integrated and flight-configured system on NIST-traceable calibrated scale. | System | Measured mass ≤ 50.0 kg with 0.1 kg resolution scale | R-092 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-C-002 | System | Constraint | Feedstock Material Constraint | The system SHALL process only Zotek F30 Aviation foam as the eligible trash input; no other waste streams shall be counted toward mass efficiency. | Per LunaRecycle Challenge TABLE 4. | Space Copy/LunaRecycle | Manufacturing Process | Material Beneficiation Processing Unit | 1-Critical | Inspection / Analysis | Review process design and material accounting records; verify only Zotek F30 is credited in mass efficiency calculation. | System | Mass efficiency calculation uses only Zotek F30 input mass as denominator; no other waste credited | R-093 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-C-003 | Component | Constraint | Processing Temperature Upper Limit | The extrusion process SHALL operate within the range of 180–220°C and SHALL NOT exceed 280°C at any point to prevent PVDF decomposition. | State-of-art advancement vs. 800–1200°C sintering approaches. | Space Copy/LunaRecycle | Thermal | Extrusion System | 1-Critical | Test / Measurement | Monitor extruder temperature throughout full cycle; verify temperature never exceeds 280°C and operates within 180–220°C range. | Component | Extruder temperature remains within 180–220°C at all times; 280°C hard limit never reached | R-094 | Draft | Not started | Thermal Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-C-004 | Component | Constraint | Nozzle Wear Life | The hardened steel extruder nozzle SHALL sustain a minimum of 100 hours of continuous operation with abrasive regolith-composite feedstock before replacement. | Wear-resistant coating required. | Space Copy/LunaRecycle | Manufacturing Process | Extrusion System | 2-High | Test / Analysis | Run nozzle accelerated wear test with abrasive regolith-composite feedstock; inspect for dimensional change and flow degradation at 100-hour mark. | Component | Nozzle dimensional wear within acceptance limits after 100 hours; no flow degradation or plugging | R-095 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-C-005 | System | Constraint | Annual Expendable Mass | Total annual expendable mass for sustained operations SHALL NOT exceed 1 kg, comprising nozzles, HEPA filters, and lubricants. | 4 nozzles (0.5 kg) + 2 HEPA filters (0.3 kg) + lubricant (0.2 kg). | Space Copy/LunaRecycle | Entire System Unit | Maintenance | 2-High | Analysis | Compile mass of all consumables required for 12-month operation using maintenance schedule; verify total ≤ 1 kg. | System | Calculated total annual expendable mass ≤ 1.0 kg per maintenance plan | R-096 | Draft | Not started | Systems / Requirements Engineering Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-C-006 | Component | Constraint | Binder Content Upper Limit | The foam-regolith composite formulation SHALL use no more than 20 wt% Zotek F30 foam as binder content to maximize regolith utilization. | Optimal binding range: 10–20% foam by mass. | Space Copy/LunaRecycle | Manufacturing Process | Mixer/Annealing | 1-Critical | Test / Analysis | Sample composite output and measure foam fraction by mass (ashing or density method); verify ≤ 20 wt%. | Component | Zotek F30 foam fraction in composite ≤ 20 wt% confirmed by mass analysis | R-097 | Draft | Not started | Materials & Extrusion Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-001 | System | Operational | Six-Phase Cycle Sequence | The system SHALL execute recycling operations in the following sequential phases: (1) Material Loading, (2) Beneficiation, (3) Extrusion Preparation, (4) Additive Manufacturing, (5) Cooling and Part Removal, (6) Post-Processing. | Phase durations: 15+30+10+120+20+15 = 210 min total. | Space Copy/LunaRecycle | Operations | Entire Printer System | 1-Critical | Demonstration | Observe full production cycle; verify each of the six phases executes in correct sequence with no phase skipped. | System | All six phases executed in prescribed sequence without omission in ≥3 consecutive cycles | R-098 | Draft | Not started | Operations Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-002 | Component | Operational | Automated Weight Verification | The system SHALL perform automated weight verification of input materials at the start of each cycle prior to initiating the beneficiation sequence. | Automated weight verification ensures the minimum batch mass requirement (AERIS-R-F-002) is confirmed before processing begins, preventing undersized cycles. | Space Copy/LunaRecycle | Controls | Sensors & Instrumentation | 2-High | Test / Demonstration | Load hopper with known masses; initiate cycle and verify system reports correct input mass prior to beneficiation. | Component | Reported input mass within ±5 g of actual mass; sequence does not proceed if mass below minimum | R-099 | Draft | Not started | Sensors & Calibration Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-003 | Subsystem | Operational | AI-Driven Process Control | The control system SHALL incorporate machine learning algorithms that continuously adjust extrusion parameters based on real-time feedstock characterization to maintain consistent output quality. | Addresses variation in input material properties. | Space Copy/LunaRecycle | Software | Firmware / Embedded Software | 2-High | Test / Demonstration | Introduce controlled variation in feedstock batch composition; verify control system adjusts extrusion parameters and output quality remains within spec. | Subsystem | Output dimensional and strength properties remain within acceptance limits despite ±5% feedstock composition variation | R-100 | Draft | Not started | Controls & Firmware Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-004 | System | Operational | Digital Twin Integration | The system SHOULD incorporate a high-fidelity digital twin simulation model for real-time process prediction and design optimization. | Developed in Month 1 of development timeline. | Space Copy/LunaRecycle | Software | Firmware / Embedded Software | 3-Medium | Analysis / Demonstration | Run digital twin simulation of full production cycle; compare predicted vs. actual process parameters for key metrics. | System | Digital twin predictions agree with measured system behavior within ±10% for key parameters (temp, torque, cycle time) | R-101 | Draft | Not started | Software Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-005 | System | Operational | In-Situ Output Characterization | The system SHALL perform dimensional verification of all output parts against CAD specifications prior to transfer to the output bin. | Part-level acceptance: ±0.5 mm structural, ±0.2 mm precision. | Space Copy/LunaRecycle | End-Use Part (EUP) | Sensors & Instrumentation | 2-High | Test / Demonstration | After each print, system automatically measures part dimensions; verify measurement occurs prior to transfer to output bin. | System | Dimensional check completed for 100% of parts prior to output bin transfer; out-of-tolerance parts flagged | R-102 | Draft | Not started | Sensors & Calibration Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-006 | System | Operational | Batch Sampling for Mechanical Testing | One in ten (1:10) produced parts from each batch SHALL be retained as representative samples for off-line mechanical testing. | Compressive (ASTM C109) and flexural (ASTM C78) testing. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 2-High | Inspection / Test | Track part count per cycle; verify 1-in-10 parts retained and labeled for off-line mechanical testing. | System | 1-in-10 parts correctly retained and labeled per production cycle across all test cycles | R-103 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-007 | Component | Operational | Thermal Cycling Qualification | Representative output samples SHALL demonstrate structural integrity after thermal cycling exposure from −40°C to +120°C. | Simulates lunar surface thermal environment. | Space Copy/LunaRecycle | End-Use Part (EUP) | Entire Printer System | 2-High | Test | Expose representative samples to thermal cycling from −40°C to +120°C for defined number of cycles; inspect for cracking, delamination, or mass change. | Component | No cracking, delamination, or >2% mass change observed after thermal cycling; strength ≥ 90% of pre-test value | R-104 | Draft | Not started | Test & Verification Lead | Initial population – v 0.0
SC-AERIS-SYS-001 | AERIS-R-O-008 | Component | Operational | Maintenance Accessibility | All consumable components (extruder nozzle, HEPA filter, lubrication points) SHALL be accessible for replacement without tools or with only standard hand tools, using a modular hot-swap design. | Quarterly nozzle swap, semi-annual HEPA replacement, annual sensor calibration. | Space Copy/LunaRecycle | Mechanical | Maintenance | 2-High | Inspection / Demonstration | Perform nozzle replacement and HEPA filter swap using only standard hand tools; time and document each operation. | Component | Each consumable replacement completed by one technician in ≤ 15 minutes with standard tools only | R-105 | Draft | Not started | Mechanical Lead | Initial population – v 0.0
SC-AERIS-R-F-009 | AERIS-R-PPM-001 | Subsystem | Performance | Robotic Arm Platform — AERIS Desktop | The PPM robotic arm for the AERIS Desktop configuration SHALL be the Universal Robots UR5e or equivalent, with a minimum reach of 850 mm, payload capacity of ≥5 kg, and positional repeatability of ±0.03 mm. | The UR5e reach of 850 mm covers the 226.3 × 226.3 mm AERIS Desktop build volume with margin. The 5 kg payload accommodates gripper and part loads of up to 3.5 kg within budget. Repeatability of ±0.03 mm supports post-processing accuracy. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 1-Critical | Inspection / Test | Verify UR5e platform datasheet against minimum reach, payload, and repeatability specifications. Validate reach coverage over full build volume by commanded motion sweep. | Component | Arm reach ≥ 850 mm; payload ≥ 5 kg; repeatability ≤ ±0.03 mm confirmed by datasheet and motion test | R-106 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-002 | Subsystem | Performance | Robotic Arm Platform — AERIS Standard | The PPM robotic arm for the AERIS Standard configuration SHALL be the Universal Robots UR10e or equivalent, with a minimum reach of 1,300 mm, payload capacity of ≥12.5 kg, and positional repeatability of ±0.05 mm. | The UR10e reach of 1,300 mm covers the 914.4 × 914.4 mm AERIS Standard build volume with margin. The 12.5 kg payload accommodates large gripper assemblies and printed parts up to 8 kg. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 1-Critical | Inspection / Test | Verify UR10e platform datasheet against minimum reach, payload, and repeatability specifications. Validate reach coverage over full build volume by commanded motion sweep. | Component | Arm reach ≥ 1,300 mm; payload ≥ 12.5 kg; repeatability ≤ ±0.05 mm confirmed by datasheet and motion test | R-107 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-003 | Component | Structural | Robotic Arm Baseplate Mounting | The robotic arm baseplate SHALL be mounted on the chamber floor using a 200 × 200 mm reinforced mounting interface compatible with both the UR5e and UR10e footprints via an adapter plate. | A standardized 200 × 200 mm baseplate interface accommodates both UR5e (149 mm base) and UR10e (190 mm base) with an adapter plate, enabling configuration commonality and reducing redesign risk between AERIS Desktop and Standard builds. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 2-High | Inspection / Analysis | Inspect baseplate dimensions and mounting hardware. Verify adapter plate compatibility with both UR5e and UR10e base diameters. Confirm load rating against maximum arm reaction loads. | Component | Baseplate measures 200 × 200 mm; adapter plate confirmed compatible with both arm variants; mounting load rating verified by analysis | R-108 | Draft | Not Started | Mechanical Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-004 | Component | Environmental | Robotic Arm Dust Protection — Sleeve Assembly | The robotic arm SHALL be protected against regolith particulate intrusion by full-arm bellows sleeves in PTFE-coated fiberglass or Nomex fabric, individual joint boots at all six joints secured with stainless steel hose clamps rated for ≥200°C continuous, and a protected cable conduit spine sealed with silicone bead at each exit point. | LHS-1D regolith simulant produces sub-10 µm particulates that are highly abrasive to joint seals, cable bundles, and encoder housings. Full-arm sleeve protection is required to prevent accelerated wear and encoder failure during post-processing operations. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 1-Critical | Inspection / Test | Inspect sleeve installation at all six joints and cable conduit routing. Expose assembled arm to representative regolith dust environment and verify no particulate ingress to joint or encoder housings after exposure. | Component | All six joints protected by boots and clamps rated ≥200°C; full-arm bellows installed; no particulate ingress at joint or encoder housings after dust exposure test | R-109 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-005 | Component | Functional | Tool Changer Dust Cover | The magnetic tool changer dock SHALL be enclosed by a hinged dust cover that opens on a command signal and remains closed during all non-swap periods to prevent regolith particulate contamination of the magnetic contact faces. | Regolith particulate contamination of the magnetic quick-swap contact faces degrades coupling force and data/power pass-through reliability. A command-actuated dust cover ensures the interface is protected during all phases except active tool exchange. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Tool Changer Unit | 1-Critical | Test / Demonstration | Command tool changer dock through a minimum of 10 open/close cycles during simulated post-processing with regolith dust present. Inspect magnetic contact faces for particulate after test. | Component | Dust cover opens on command and closes after each tool swap; magnetic contact faces show no regolith contamination after 10-cycle dust exposure test | R-110 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-006 | Component | Functional | End Effector — Small Gripper | The PPM end effector suite SHALL include a small gripper with a jaw span of ≥80 mm and adjustable gripping force in the range of 5–30 N, compatible with the UR5e payload budget, for precision part retrieval and small component handling. | A small gripper enables precision handling of small printed parts, fasteners, and components within the AERIS Desktop build volume. The 5–30 N adjustable force range prevents part damage while ensuring secure grip on fragile regolith-composite outputs. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 1-Critical | Test / Inspection | Measure small gripper jaw span at full open. Test gripping force at min and max settings with calibrated force gauge. Verify combined gripper + part mass is within UR5e 5 kg payload budget. | Component | Jaw span ≥ 80 mm; gripping force adjustable 5–30 N confirmed by force gauge; combined gripper + part load within UR5e 5 kg payload budget | R-111 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-007 | Component | Functional | End Effector — Large Gripper | The PPM end effector suite SHALL include a large gripper with a jaw span of ≥200 mm and adjustable gripping force in the range of 20–80 N, capable of handling printed parts up to 8 kg, for full-part extraction from the build plate and transfer to the collection bin. | Full-part extraction from the AERIS Standard build plate requires a large gripper capable of handling parts up to 8 kg with sufficient jaw span for the maximum output geometry. The 20–80 N adjustable force range provides secure grip across the range of part sizes and densities. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 1-Critical | Test / Inspection | Measure large gripper jaw span at full open. Test gripping force at min and max settings with calibrated force gauge. Demonstrate extraction and bin transfer of a representative maximum-mass part. | Component | Jaw span ≥ 200 mm; gripping force adjustable 20–80 N; successful extraction and bin transfer of part up to 8 kg with no drop or damage | R-112 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-008 | Component | Functional | End Effector — Saw | The PPM end effector suite SHALL include a motorized saw end effector (rotary or oscillating, final type subject to material hardness testing) with a maximum cut depth of ≥30 mm driven by a brushless DC motor operating on a 12V rail, for support structure cutting and overhang trimming. | Support structure removal from regolith-composite parts requires a motorized cutting tool capable of reaching a minimum 30 mm depth. A brushless DC motor on the 12V rail ensures compatibility with the AERIS power architecture and eliminates brush-wear maintenance concerns. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 1-Critical | Test / Inspection | Verify saw motor operates on 12V DC rail. Measure maximum cut depth on representative regolith-composite support structure material. Confirm successful support removal on a printed test part. | Component | Saw operates on 12V DC; maximum cut depth ≥ 30 mm on representative material; support structures fully removed from representative printed test part | R-113 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-009 | Component | Functional | End Effector — Scraper | The PPM end effector suite SHALL include a passive spring-loaded carbide blade scraper with a contact force compliance range of 5–15 N for surface finishing, adhesion layer removal, and burr cleanup on printed parts. | A passive spring-loaded scraper provides surface finishing without a motorized drive, reducing mass, complexity, and failure modes. The 5–15 N passive compliance range prevents gouging of printed part surfaces while providing sufficient force for adhesion layer and burr removal. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Robotic Arm | 2-High | Test / Inspection | Verify scraper contact force using calibrated force gauge across full spring travel range. Demonstrate surface finishing on representative printed part; inspect for quality improvement and absence of gouging. | Component | Passive contact force within 5–15 N range across spring travel; surface finish improved on representative part with no gouging or unintended material removal | R-114 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-010 | Subsystem | Functional | PPM Thermal Trigger Logic | The PPM control system SHALL incorporate thermal sensor-based trigger logic that prevents robotic arm activation until the printed part and print chamber have reached a defined safe handling temperature threshold, as monitored by the thermal sensor array. | Activating the robotic arm on an inadequately cooled part risks part deformation during gripper contact, end effector thermal damage, and crew burn hazard during part transfer. Temperature-gated arm activation ensures part integrity and crew safety. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Sensors & Instrumentation | 1-Critical | Test / Demonstration | Command arm activation while chamber temperature is above the safe handling threshold; verify arm does not activate. Allow chamber to cool to threshold; verify arm activates automatically. Repeat for ≥3 consecutive cycles. | Subsystem | Arm does not activate above safe handling temperature threshold; arm activates automatically once threshold is reached; confirmed across ≥3 consecutive cycles | R-115 | Draft | Not Started | Controls & Firmware Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-011 | Subsystem | Functional | IPC/HMI Supervisory Control Architecture | The PPM SHALL be controlled by a dedicated IPC/HMI supervisory processor architecturally separate from the MBU and gantry subsystem controllers, capable of integrating up to 364 sensors and cameras simultaneously with real-time error detection, and interfacing with an LED touchscreen HMI for operator monitoring and cycle intervention. | A dedicated supervisory IPC separate from subsystem-level controllers limits fault propagation — a PPM control layer failure cannot cascade to MBU or gantry controllers. Real-time simultaneous monitoring of up to 364 sensors/cameras eliminates sequential polling latency. The LED HMI supports non-expert operation per OR-1. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Software | Firmware / Embedded Software | 1-Critical | Test / Analysis | Induce a simulated IPC fault and confirm no impact to MBU or gantry operation. Inject faults on ≥10 sensors/cameras simultaneously and confirm real-time detection on HMI within 1 second of injection. | Subsystem | IPC fault produces no effect on MBU or gantry controllers; simultaneous fault detection confirmed for ≥10 injected faults; all faults displayed on HMI within 1 second | R-116 | Draft | Not Started | Controls & Firmware Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-012 | Component | Safety | PPM E-Stop Hardwired Integration | The PPM E-stop signal SHALL be hardwired across all PPM motor drivers and heater relays such that E-stop activation immediately halts all robotic arm motion and associated heater outputs independent of software state. | A software-only E-stop is insufficient for a crewed environment. Software faults or latency could prevent timely halt. Hardwired E-stop across all motor drivers and heater relays ensures crew protection is never dependent on software execution path, consistent with applicable machine safety standards and AERIS-R-S-006. | AERIS PPM Robotic Arm Technical Overview Rev 1; AERIS-R-S-006 | Robotic Arm | Safety System | 1-Critical | Test / Inspection | Activate E-stop during active arm motion and verify all PPM motor drivers de-energize within 500 ms. Inspect wiring to confirm E-stop circuit is hardwired to all motor drivers and heater relays independent of software. | Component | All PPM motor drivers and heater relays de-energize within 500 ms of E-stop activation; hardwired circuit confirmed by wiring inspection; behavior verified independent of software state | R-117 | Draft | Not Started | Safety & Reliability Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-013 | Subsystem | Performance | PPM Subsystem Mass Budget | The total PPM subsystem mass, including the robotic arm body, end effector suite, tool changer dock, dust sleeve assembly, and all mounting hardware, SHALL NOT exceed 10.0 kg as allocated in the AERIS-R Mass Equipment List (MEL). | The AERIS-R system total mass is constrained to 50 kg per AERIS-R-C-001. The PPM subsystem allocation of 10.0 kg per the proposal MEL must be maintained to preserve margin across all subsystem allocations and ensure the system-level mass constraint is not violated. | AERIS PPM Robotic Arm Technical Overview Rev 1; SPACECOPY_AERIS-R LunaRecycle Phase 2 Proposal | Robotic Arm | Robotic Arm | 1-Critical | Measurement (calibrated scale) | Weigh fully integrated PPM subsystem including arm body, all end effectors, tool changer dock, dust sleeve assembly, and all mounting hardware on a calibrated scale. | Subsystem | Total PPM subsystem measured mass ≤ 10.0 kg on calibrated scale | R-118 | Draft | Not Started | Systems / Requirements Engineering Lead | Initial population – PPM Rev 1 Technical Overview
SC-AERIS-R-F-009 | AERIS-R-PPM-014 | Component | Functional | Support Structure Waste Recycling Interface | The robotic arm SHALL deposit all support structures removed during post-processing into a dedicated recyclable waste container that is interface-compatible with re-feeding into the Phase 1 MBU processing sequence. | Support structures removed during post-processing represent usable regolith-composite material. Depositing them into a recyclable container for re-introduction into the MBU feedstock stream reduces material waste, improves mass efficiency, and supports the closed-loop ISRU manufacturing philosophy of the AERIS-R system. | AERIS PPM Robotic Arm Technical Overview Rev 1 | Robotic Arm | Waste Handling / Recycling Module | 2-High | Inspection / Demonstration | Run full post-processing cycle; verify all support structures are deposited into the designated recyclable waste container with none discarded. Verify container interface is compatible with MBU Phase 1 re-feed port. | Component | 100% of removed support structures deposited in recyclable waste container; 0 kg support waste discarded; container confirmed compatible with MBU Phase 1 re-feed interface | R-119 | Draft | Not Started | Motion Systems Lead | Initial population – PPM Rev 1 Technical Overview
End | End | End | End | End | End | End | End | End | End | End | End | End | End | End | End | End | End | End | End

## Req Header Legend (hidden)
Requirements Headers
Requirement ID
Requirement Level
Parent Requirement ID
Requirement Type
Requirement Statement
Rationale / Intent
Source
Affected System Element
Verification Method
Verification Description
Verification Level
Success Criteria
Risk ID(s)
Compliance Status
Verification Status
Owner
Change History / Notes

## Classification List
Requirement Level | Requirement Type | Affected System Discipline | Affected System/Subsystem/Component Element | Priority | Verification Method | Verification Level | Compliance Status | Verification Status | Owner
Mission | Constraint | Communications | Actuators & Motors | 1-Critical | Analysis | Assembly | Compliant | Failed | Controls & Firmware Lead
Operational | Electrical | Controls | Binder Intake | 2-High | Demonstration | Component | Draft | In Progress | Electrical / Power Lead
System | Environmental | End-Use Part (EUP) | Build Platform / Print Bed | 3-Medium | Inspection | Flight Test | Non-Compliant | Not Applicable (N/A) | Integration Lead
Segment | Functional | Entire System Unit | Calibration System | 4-Low | Test | Ground Test | Not Applicable (N/A) | Not Started | Manufacturing Lead
Subsystem | Human Factors | External Support Equipment (ESE) | Communications Interface |  |  | Mission | Partially Compliant | Re-Test Required | Materials & Extrusion Lead
Assembly | Interface | External System | Compact Sieve |  |  | Segment | TBD | Verified | Mechanical Lead
Component | Maintainability | Interface (External) | Control Electronics |  |  | Simulation | Waiver Approved | Waived | Motion Systems Lead
| Operation | Interface (Internal) | Data Handling / Logging |  |  | Subsystem | Waiver Requested |  | Operations Lead
| Performance | Manufacturing Process | Entire Printer System |  |  | System |  |  | Product Manager
| Regulatory / Standards | Mechanical | Environmental Control / Enclosure | [5 empty] | Program Manager
| Reliability | Operations | Extrusion System | [5 empty] | Quality & Configuration Management
| Safety | Power | Firmware / Embedded Software | [5 empty] | Safety & Reliability Lead
| Software | Software | Gantry/Enclosure | [5 empty] | Sensors & Calibration Lead
| Structural | Structure | Maintenance | [5 empty] | Software Lead
| Thermal | Thermal | Material Beneficiation Processing Unit | [5 empty] | Supplier / Vendor Owner
|  |  | Material Feed System | [5 empty] | Systems / Requirements Engineering Lead
|  |  | Material Identification | [5 empty] | Test & Verification Lead
|  |  | Material Storage & Handling | [5 empty] | Thermal Lead
Mixer/Annealing
Motion System (X/Y/Z)
Multi-Material Switching System
Power System
Print Head
Robotic Arm
Rotational Motion System (Pitch, Yaw, Roll)
Safety System
Sensors & Instrumentation
Structural Frame
Thermal Control System
Thermal Sensors/Cameras
Tool Changer Unit
User Interface (HMI)
Waste Handling / Recycling Module
Wire Filament Maker

## Classificaiton Explanation
Classification List Explanation
Requirement Level (Column C)
Requirement Level | Definition (Engineering / Systems Context) | Scope Focus | Typical Author
Mission | Defines the overarching purpose, goals, and success outcomes of the overall program or system in its operational environment. | Why the system exists | Stakeholders / Program / Mission Analysis
Operational | Describes how the system must behave during real-world use, including workflows, scenarios, and user interactions. | Real-world use and scenarios | Systems Engineering / Ops Concept
System | Specifies capabilities and performance of the complete integrated system as a whole. | Entire product/system boundary | Systems Engineering
Segment | Defines requirements for a major functional partition of the system (e.g., ground segment, flight segment, space segment). | Major architecture partition | Systems Architecture
Subsystem | Covers requirements for a major functional grouping within the system (e.g., power, propulsion, thermal, avionics). | Functional engineering domains | Subsystem Leads
Assembly | Requirements for a grouped set of components forming a functional unit within a subsystem. | Hardware grouping | Mechanical / Electrical Design
Component | Defines requirements for individual parts or modules that cannot be further decomposed without losing independent function. | Single hardware or logical unit | Design Engineers
Interface | Specifies interactions between systems, subsystems, components, software, or users including data, mechanical, electrical, or environmental exchanges. | Boundaries and interactions | Systems / Integration Engineers
Software | Defines functional and non-functional requirements for code-based behavior including algorithms, logic, timing, and data handling. | Digital behavior | Software Engineering
Requirement Type (Column D)
Requirement Type | Definition (Engineering Context) | What It Controls | Typical Verification
Constraint | A limitation imposed on design, materials, processes, cost, schedule, or architecture that restricts solution space without defining system behavior. | Boundaries on design freedom | Inspection / Analysis
Electrical | Requirements governing electrical characteristics including power, voltage, current, grounding, EMI/EMC, and signal integrity. | Electrical performance & compatibility | Test / Analysis
Environmental | Requirements defining conditions the system must withstand or operate within (temperature, humidity, vibration, radiation, dust, altitude). | Operating/survival conditions | Environmental Test
Functional | Defines actions or capabilities the system must perform to achieve intended behavior or mission objectives. | What the system does | Test / Demonstration
Human Factors | Requirements ensuring usability, ergonomics, accessibility, workload limits, and safe human interaction with the system. | Human-system interaction | Demonstration / Inspection
Interface | Defines mechanical, electrical, data, or environmental exchanges between systems, subsystems, software, or users. | Boundaries & interactions | Test / Inspection
Maintainability | Requirements governing ease, time, tools, and procedures required for maintenance, repair, or replacement. | Sustainment efficiency | Demonstration / Analysis
Operation | Defines operational behaviors, modes, procedures, workflows, or system responses during use. | How system is operated | Demonstration
Performance | Specifies measurable quantitative attributes such as speed, capacity, accuracy, throughput, efficiency, or response time. | Quantifiable outcomes | Test / Analysis
Regulatory / Standards | Requirements mandating compliance with external standards, laws, certifications, or governing authorities. | Legal/compliance obligations | Inspection / Certification
Reliability | Requirements defining probability of failure, uptime, MTBF (mean time between failures), or lifecycle durability. | Consistent operation over time | Analysis / Test
Safety | Requirements that prevent hazards, reduce risk, or mitigate harm to personnel, equipment, or environment. | Hazard prevention | Analysis / Test
Software | Requirements defining digital logic, algorithms, data handling, interfaces, timing behavior, and software constraints. | Code-driven behavior | Test / Analysis
Structural | Requirements governing mechanical strength, stiffness, load capacity, deformation limits, and mechanical integrity. | Physical robustness | Structural Test / Analysis
Thermal | Requirements controlling heat generation, transfer, dissipation, insulation, and operating temperature limits. | Temperature behavior | Thermal Test / Analysis
Affected System Discipline (Column H)
Discipline | Definition (Engineering Context) | Primary Scope / Ownership
Communications | Requirements affecting data transmission, telemetry, networking, RF links, signal protocols, bandwidth, and communication hardware/software. | Comms Engineering / Avionics
Controls | Requirements impacting control algorithms, feedback loops, stability, actuation logic, automation, and system response behavior. | Controls / GNC / Automation Engineering
End-Use Part (EUP) | Requirements directly affecting the final product or output component delivered to the user or mission customer. | Product Engineering / Payload / Deliverable Hardware
Entire System Unit | Requirements impacting the full integrated system across all subsystems rather than a specific discipline or component. | Systems Engineering / Integration
External Support Equipment (ESE) | Requirements related to ground support tools, maintenance equipment, test rigs, transport fixtures, or operational support hardware. | Ground Systems / Test / Operations Engineering
External System | Requirements affecting third-party systems or external platforms that must interact with the primary system. | Integration / Systems Engineering
Interface (External) | Requirements governing interactions between the system and external entities (users, other systems, infrastructure, environment). | Systems Integration
Interface (Internal) | Requirements governing interactions between internal subsystems, assemblies, components, or software modules. | Integration / Architecture
Manufacturing Process | Requirements affecting fabrication methods, assembly procedures, production constraints, tolerances, materials processing, or quality control. | Manufacturing / Production Engineering
Mechanical | Requirements impacting moving parts, mechanisms, kinematics, housings, tolerances, and physical mechanical design. | Mechanical Engineering
Operations | Requirements affecting system use, procedures, workflows, maintenance actions, and real-world operational behavior. | Operations / Systems Engineering
Power | Requirements impacting electrical power generation, storage, conversion, distribution, grounding, or energy budgets. | Electrical / Power Systems Engineering
Software | Requirements affecting code, algorithms, logic behavior, timing, data handling, firmware, and digital control systems. | Software Engineering
Structure | Requirements affecting load-bearing elements, strength, stiffness, fatigue life, deformation limits, and structural integrity. | Structural Engineering
Thermal | Requirements impacting heat transfer, cooling systems, insulation, temperature regulation, and thermal environments. | Thermal Engineering
Affected System / Subsystem / Component Element (Column I)
Element | Definition (Engineering Context)
Actuators & Motors | Devices that produce motion or force in response to control inputs, including electric motors, linear actuators, servos, and stepper motors.
Binder Intake | System or mechanism that accepts and delivers binder materials into the additive manufacturing or material processing system.
Build Platform / Print Bed | The surface or stage on which parts are formed, deposited, or printed, often including leveling and heating functions.
Calibration System | Components and procedures used to verify and adjust system parameters to ensure accurate operation and dimensional fidelity.
Communications Interface | Hardware and protocols enabling data transfer between system modules or between the system and external entities.
Compact Sieve | Device used to filter, size, or separate granular or powdered materials prior to processing.
Control Electronics | Circuitry and embedded systems responsible for controlling actuators, sensors, and overall system operation.
Data Handling / Logging | Systems and subsystems that collect, store, process, and transmit operational or sensor data for analysis, diagnostics, or reporting.
Entire Printer System | The complete additive manufacturing system as an integrated unit, including all hardware, software, and subsystems.
Environmental Control / Enclosure | Systems maintaining temperature, humidity, air flow, and containment conditions for process stability and safety.
Extrusion System | Components responsible for material deposition, melting, or extrusion during the printing process.
Firmware / Embedded Software | Low-level software directly controlling hardware operation, timing, and real-time process logic.
Gantry / Enclosure | Structural assembly providing motion guidance and support for system modules, often including protective enclosure features.
Maintenance | Processes, tools, and interfaces for inspection, repair, cleaning, or replacement of components and assemblies.
Material Beneficiation Processing Unit | Subsystem that conditions, purifies, or modifies raw materials to meet required specifications before printing.
Material Feed System | Mechanisms that deliver raw materials from storage to the processing or printing system.
Material Identification | Subsystem responsible for verifying material type, properties, and suitability for processing.
Material Storage & Handling | Containers, hoppers, silos, and transfer systems for storing and managing raw and processed materials.
Mixer / Annealing | Equipment that blends, conditions, or thermally treats materials to achieve required homogeneity or physical properties.
Motion System (X/Y/Z) | Mechanical assemblies that enable controlled linear movement in the X, Y, and Z axes for positioning or printing.
Multi-Material Switching System | Mechanism that allows selection, switching, or delivery of multiple materials into the processing system.
Power System | Subsystem responsible for supplying, conditioning, and distributing electrical power to all system modules.
Print Head | The portion of the printer that directly deposits material onto the build platform, including nozzles and heaters.
Robotic Arm | Multi-degree-of-freedom manipulator used to move tools, materials, or components with precision.
Rotational Motion System (Pitch, Yaw, Roll) | Assemblies enabling angular motion or orientation of components or subsystems about one or more axes.
Safety System | Components and procedures designed to prevent injury, damage, or hazardous conditions during operation.
Sensors & Instrumentation | Devices that measure physical, electrical, or environmental variables and provide feedback for control or monitoring.
Structural Frame | The primary load-bearing skeleton of the system, providing support and rigidity for all subsystems.
Thermal Control System | Assemblies and mechanisms that regulate temperature through heating, cooling, or insulation.
Thermal Sensors / Cameras | Devices that monitor temperature, heat flux, or thermal imagery for process control and safety.
Tool Changer Unit | Mechanism that allows automatic or manual switching of different tools or end-effectors during operation.
User Interface (HMI) | Hardware and software that allow operators to interact with, monitor, and control the system.
Waste Handling / Recycling Module | Subsystem that collects, processes, and disposes or recycles material waste from the system.
Wire Filament Maker | Equipment that converts raw material into filament or wire form for use in additive manufacturing processes.
Verfication Method (Column J)
Verification Method | Definition (Engineering Context) | Typical Use Cases | Evidence Produced
Analysis | Verification performed by mathematical, logical, or computational evaluation without physical execution. This includes modeling, simulations, calculations, and algorithmic validation. | Performance predictions, thermal modeling, structural stress calculations, software algorithm correctness. | Reports, calculation sheets, simulation logs, model outputs.
Demonstration | Verification by showing that a system or component can perform the intended function in a controlled or operational scenario without full measurement of quantitative parameters. | Operational procedures, workflow validation, human factors, maneuver sequences, software GUI behavior. | Observation records, procedure checklists, demonstration videos, log notes.
Inspection | Verification through visual, dimensional, or procedural examination to confirm attributes, configuration, completeness, or compliance with standards. | Mechanical dimensions, assembly correctness, labeling, documentation compliance, surface finish, workmanship. | Inspection reports, photographs, measured dimensions, checklists.
Test | Verification performed by executing controlled experiments to measure system behavior against quantitative criteria. Includes functional, performance, environmental, integration, and acceptance tests. | Thermal tests, vibration, electrical load testing, material property testing, software functional verification. | Test reports, raw data logs, measurement readings, pass/fail assessment.
Verfication Level (Column L)
Verification Level | Definition (Engineering Context) | Typical Scope / Application
Assembly | Verification performed on a functional grouping of components that operate together as a unit but do not represent the full subsystem. | Example: motor assembly, calibration system assembly, material feed assembly.
Component | Verification performed on individual parts or modules to ensure they meet specified requirements independently of assemblies or subsystems. | Example: actuator, sensor, electronic board, nozzle.
Flight Test | Verification performed under actual operational flight conditions, evaluating system or subsystem behavior in the real mission environment. | Example: spacecraft or aircraft in orbit or during test flight.
Ground Test | Verification performed in a controlled terrestrial environment that simulates operational conditions without being in actual flight. | Example: vibration, thermal vacuum, environmental chamber, or hardware-in-the-loop testing.
Mission | Verification performed at the level of the overall operational objective, often considering mission success criteria rather than isolated measurements. | Example: satellite successfully delivering payload to orbit.
Segment | Verification performed on a defined portion of the system architecture, such as a functional segment (ground segment, flight segment, control segment). | Example: ground control network performance, telemetry segment functionality.
Simulation | Verification performed using models or computational environments to replicate system or component behavior under expected operational conditions. | Example: trajectory simulation, thermal model, software-in-the-loop test.
Subsystem | Verification performed on a functional grouping of assemblies that together provide a specific capability within the system. | Example: power subsystem, motion subsystem, thermal subsystem.
System | Verification performed on the fully integrated and operational system to ensure all requirements are met collectively. | Example: fully assembled printer, spacecraft, or additive manufacturing system performing as intended.
Difference between Requiment Level vs Verificaiton Level Classification
Concept | Definition | Focus | Example
Requirement Level | The hierarchical scope or abstraction at which the requirement is written. It tells you what part of the system the requirement applies to. | Ownership, design scope, and traceability | System-level: The spacecraft shall deliver 500 kg to orbit.
Subsystem-level: The propulsion subsystem shall produce 20 kN thrust.
Component-level: The nozzle shall withstand 1500°C.
Verification Level | The level at which you actually verify that the requirement is satisfied. It tells you where and how you test, inspect, or simulate. | Verification planning, test resource, method selection | System-level: Full spacecraft test in integrated configuration.
Subsystem-level: Propulsion subsystem tested on a test stand.
Component-level: Nozzle tested in lab furnace.
Compliance Status (Column O)
Compliance Status | Definition (Engineering Context) | Notes / Typical Usage
Compliant | The requirement has been fully satisfied and verified according to the verification method and level. | Evidence is available (test report, analysis, inspection, or demonstration).
Draft | The requirement has been written or proposed but has not yet been approved, baselined, or verified. | Usually in development or review; not yet formally accepted.
Non-Compliant | The requirement has been evaluated and cannot be met as written. | May trigger engineering change, design modification, or formal waiver.
Not Applicable (N/A) | The requirement does not apply to this system, subsystem, or component. | Used to clarify scope; must be justified.
Partially Compliant | The requirement is partially satisfied, but some elements are unmet or outside specification limits. | Usually requires mitigation plan or exception documentation.
TBD (To Be Determined) | Compliance cannot yet be evaluated due to insufficient data, design definition, or verification results. | Common for early-stage or conceptual requirements.
Waiver Approved | A formal authorization has been granted to deviate from or not meet the requirement. | Typically requires documentation of rationale, risk acceptance, and authority approval.
Waiver Requested | A formal request has been submitted to approve deviation from the requirement, pending authority review. | Indicates a compliance exception is under consideration.
Verificaiton Status (Column P)
Verification Status | Definition (Engineering Context) | Notes / Typical Usage
Failed | The verification activity was performed, and the requirement did not meet the specified criteria. | Typically triggers corrective actions, redesign, or re-test.
In Progress | Verification activity has started but is not yet complete. | May include ongoing tests, analysis, or inspections.
Not Applicable (N/A) | Verification is not required for this requirement due to its scope, relevance, or exclusion. | Must be justified; often used for conditional requirements.
Not Started | Verification activity has not yet been initiated. | Indicates planned but pending verification.
Re-Test Required | Verification was attempted but results were inconclusive, invalid, or require confirmation. | Often used when test setup, instrumentation, or environmental conditions were insufficient.
Verified | The requirement has been successfully verified according to the specified verification method and level. | Evidence exists: test reports, analysis results, inspection documentation, or demonstration records.
Waived | Verification has been formally excused or skipped via approved waiver, typically because the requirement is not feasible, critical, or redundant. | Must reference waiver documentation and approval authority.
Compliance Status vs Verification Status Difference
Aspect | Compliance Status | Verification Status
Focus | Whether the requirement is met | Whether the verification activity has been executed and its outcome
Examples | Compliant, Non-Compliant, Partially Compliant | Verified, Failed, In Progress, Not Started
Action | May trigger design changes, waivers, or mitigation | Tracks test progress, repeats, or waiver decisions
Timing | Assessed after verification | Assessed during or immediately after verification activity
Owner (Column Q)
Owner | Definition / Responsibility
Controls & Firmware Lead | Responsible for design, implementation, and verification of control systems and embedded firmware, including feedback loops, real-time control logic, and actuation algorithms.
Electrical / Power Lead | Responsible for power generation, distribution, conditioning, wiring, and electrical interfaces across the system, including compliance with electrical requirements.
Integration Lead | Responsible for ensuring subsystems, assemblies, and components are correctly integrated, interfaces are satisfied, and system-level functionality is achieved.
Manufacturing Lead | Oversees fabrication, assembly, production processes, tooling, and quality assurance for manufacturability requirements.
Materials & Extrusion Lead | Responsible for material handling, identification, processing, extrusion, and delivery systems, including compliance with material specifications.
Mechanical Lead | Responsible for mechanical design, assemblies, motion mechanisms, structural interfaces, and mechanical integrity of the system.
Motion Systems Lead | Responsible for all linear, rotational, and robotic motion systems, including actuators, motors, gantries, and multi-axis motion control.
Operations Lead | Ensures system operational procedures, workflows, human factors, and mission operations are correctly defined and supported.
Product Manager | Provides oversight for product definition, scope, requirements alignment, market or customer priorities, and overall product success.
Program Manager | Accountable for schedule, budget, resource allocation, risk management, and overall program execution to meet objectives.
Quality & Configuration Management | Responsible for ensuring that requirements, design changes, and verification activities follow quality processes and configuration control.
Safety & Reliability Lead | Ensures safety, risk mitigation, hazard analysis, reliability engineering, and compliance with regulatory safety standards.
Sensors & Calibration Lead | Responsible for all sensors, measurement devices, instrumentation, and calibration systems ensuring accuracy, reliability, and traceability.
Software Lead | Responsible for software development, verification, integration, and alignment with system requirements, including application-level software and control logic.
Supplier / Vendor Owner | Responsible for managing external vendors or suppliers providing components, assemblies, or services to meet requirements.
Systems / Requirements Engineering Lead | Ensures requirements are properly captured, traceable, consistent, and verified, and supports system-level design and integration activities.
Test & Verification Lead | Responsible for planning, executing, and documenting verification activities (analysis, test, inspection, demonstration) across all system levels.
Thermal Lead | Responsible for thermal control systems, heat management, insulation, temperature monitoring, and compliance with thermal requirements.

## Discipline Element Matrix
Element X Discipline Matrix Organizaiton |  | Discipline
|  | Entire System Unit | End-Use Part (EUP) | Structure | Power | Thermal | Controls | Software | Communications | Mechanical | Manufacturing Process | External Support Equipment (ESE) | Operations | External System | Interface (Internal) | Interface (External)
Elements | Entire Printer System
Print Head
Extrusion System
Material Feed System
Build Platform / Print Bed
Motion System (X/Y/Z)
Rotational Motion System (Pitch, Yaw, Roll)
Actuators & Motors
Structural Frame
Thermal Control System
Power System
Control Electronics
Firmware / Embedded Software
User Interface (HMI)
Sensors & Instrumentation
Calibration System
Multi-Material Switching System
Material Storage & Handling
Environmental Control / Enclosure
Waste Handling / Recycling Module
Safety System
Communications Interface
Data Handling / Logging
Maintenance
Gantry/Enclosure
Material Beneficiation Processing Unit
Mixer/Annealing
Compact Sieve
Binder Intake
Wire Filament Maker
Thermal Sensors/Cameras
Robotic Arm
Material Identification
Tool Changer Unit
Legend
SC: Space Copy
QES: Quartus Engineering Solution
ZES: Zephyrus Engineering Solutions
MAI: Motion AI